## Sheet1
Allied Fencing & Services
support@alliedfencingandservices.com
(915) 777-0079
INFO | Name / Nombre | Kenneth
| Address / Dirección | 808 Brisa Del Mar Drive, El Paso, TX 79912
| Date / Fecha | Dec/10/2024
| Installer(s) / Instalador(er) | Pedro, Cesar
SCOPE OF WORK | Specifications / Especificaciones
| Fence Type Tipo de Cerca | Floating Chain Link Fence 11.5 gauge chain link fabric
| Fence Height Altura de la Cerca | 4ft
| Fence Length Longitud de la Cerca | 40 linear feet.
| Post Material Material de los Postes | Schedule 20 posts
| Panel/Slat Type Tipo de Panel | Brown Privacy Bottom Lock Slats
Additional Features Características Adicionales
GATES | Gate Puerta # | Gate Type Tipo de Puerta | Dimensions Dimensiones | Material Material | Style Estilo | Swing Direction Dirección de Apertura
| Gate 1 Puerta 1 |  | ____ x ____
| Gate 2 Puerta 2 |  | ____ x ____
| Gate 3 Puerta 3 |  | ____ x ____
| Gate 4 Puerta 4 |  | ____ x ____
PRE-INSTALL | Task Tarea | Completed Completado | Notes Notas
Customer approves layout Cliente aprueba diseño
Underground utilities marked Utilidades marcadas
Property lines confirmed Líneas de propiedad
Site cleared of obstacles Sitio despejado
Materials and tools checked Materiales y herramientas revisadas
INSTALLATION | Task / Tarea | Completed Completado | Notes Notas
Posts set to correct depth Postes a la profundidad correcta
Posts level, plumb, aligned Postes nivelados, plomados y alineados
Concrete footing complete Zócalo de concreto completo
Panels evenly spaced Paneles espaciados uniformemente
Fasteners secure, no damage Sujetadores seguros, sin daños
Consistent height maintained Altura consistente mantenida
Gate posts reinforced, level Postes de puerta reforzados, nivelados
Gate operates smoothly Puerta opera suavemente
Proper clearance for gates Despeje adecuado para las puertas
No sharp edges or fasteners Sin bordes afilados ni sujetadores
Sections sturdy and stable Secciones firmes y estables
POST-INSTALL | Task Tarea | Completed Completado | Notes Notas
Uniformity and alignment Uniformidad y alineación
Adjustments made as needed Ajustes realizados según sea necesario
Site cleaned of debris Sitio limpio de escombros
Customer walkthrough complete Recorrido con el cliente completado
NOTES | Additional Notes Notas Adicionales
Each Post is cemented into the ground.
Floating fence on the back yard to the front yard. Small floating fence on the piece of Rockwall that separates the front and the back.
3 Terminal Posts, 2 line posts, tension wire, and top rail.
Brown 4ft Bottom lock slats
| Customer Signature |  |  | Date